Phase 0 Pilot Plan

Establishing the CSED Phenomenon: A Go/No-Go Study

Abhinav Shukla

CSVTU Bhilai  ·  ISI Kolkata  ·  IIIT Hyderabad

August 2026

# 1. Purpose and Scope

Phase 0 exists to answer one question as cheaply as possible: does Cross-Paradigm Explanation Divergence (CSED) behave as a real, measurable phenomenon, and does it survive an attacker who knows about it? Everything in this document is scoped to answer that question in 2–3 weeks on a single GPU, using existing pretrained models rather than training anything from scratch. Nothing here is meant to produce publishable numbers — it is meant to tell you, quickly and honestly, whether the rest of the proposal is worth building.

This is a go/no-go study. Its output is a decision, not a paper draft: either “the phenomenon holds under adaptive attack, proceed to Phase 1,” or “it doesn't, here is what we learned and what to try instead.” Both outcomes are a successful Phase 0.

# 2. What Phase 0 Deliberately Does Not Cover

Keeping this list explicit is what keeps the pilot to 2–3 weeks. None of the following belong in Phase 0, even though they appear later in the full proposal:

- No training-time regularization or modification of either detector — both are used exactly as pretrained and released.

- No trajectory-based divergence (CSED across PGD iteration steps) — that is a Phase 1/2 extension once the static signal is validated.

- No T3 (explanation-targeted, eXIAA-style) attacks — Phase 0 only tests T1 and, conditionally, T2.

- No learned MLP classifier over multiple features — Phase 0 uses CSED alone, measured directly, so the result is easy to interpret.

- No NTIRE 2026 benchmark submission or cross-generator sweep — a small, fixed dataset is enough to answer the go/no-go question.

# 3. Go / No-Go Success Criteria

Decide these numbers before running anything, not after looking at results. The bars below are illustrative starting points — adjust them to your risk tolerance, but write down your chosen numbers in advance and do not move them after seeing the data.

| Question | Test | Illustrative bar |
| --- | --- | --- |
| Q1 — Observation: is CSED stable on clean data? | Split clean data in half; compare CSED distributions between the two halves (negative control). | AUC of clean-split-A vs. clean-split-B should be ≈ 0.5 (i.e., indistinguishable). If not, CSED is too noisy to proceed. |
| Q2 — Hypothesis: does CSED shift under T1? | Compare CSED distribution on clean vs. FGSM/PGD-attacked images; KS-test + AUC of CSED as a clean-vs-attacked classifier. | AUC ≥ 0.65–0.70 and KS-test p < 0.05 treated as a promising signal worth continuing to Q3. |
| Q3 — Gate: does the Q2 result survive an adaptive, CSED-aware attack (T2)? | Re-run the comparison using images attacked with a joint objective that also suppresses CSED. | AUC noticeably above 0.5 (e.g., ≥ 0.60) after adaptive suppression → proceed to Phase 1. At or near 0.5 → report as a negative/partial result; do not proceed to full build-out. |

# 4. Components, Models, and Tools

Everything below is an existing, pretrained, publicly released component. Phase 0 should involve no new model training.

| Component | Choice | Source |
| --- | --- | --- |
| Paradigm 1 (artifact/frequency) | NPR (Neighboring Pixel Relationships), CVPR 2024 | github.com/chuangchuangtan/NPR-DeepfakeDetection — lightweight CNN, pretrained weights and inference script included |
| Paradigm 2 (semantic) | UnivFD (CLIP ViT-L/14 linear probe), CVPR 2023 | github.com/Yuheng-Li/UniversalFakeDetect (mirrored at WisconsinAIVision/UniversalFakeDetect) — pretrained model + eval script included |
| Explanation extraction | Grad-CAM (CNN); Grad-CAM with reshape_transform (ViT) | github.com/jacobgil/pytorch-grad-cam — supports both CNN target layers and transformer patch-token outputs |
| T1 attacks (FGSM, PGD) | torchattacks | github.com/Harry24k/adversarial-attacks-pytorch — pip install torchattacks |
| T2 adaptive attack | Custom PGD loop (not off-the-shelf) | Hand-written: joint loss = classification loss − λ·CSED, since no library supports a CSED-aware objective out of the box |
| Distance metric D | Cosine distance (primary), JS divergence (check) | Implement directly with numpy/scipy on normalized saliency maps |

### 4.1 A note on Grad-CAM for the semantic stream

NPR is a plain CNN, so standard Grad-CAM on its last convolutional layer works out of the box. UnivFD is a frozen CLIP ViT-L/14 backbone with a small linear probe on top, which is not a CNN — Grad-CAM needs to be applied to the transformer's patch-token output and reshaped back into a spatial map. pytorch-grad-cam documents a reshape_transform argument specifically for this; budget real time in Week 1 to get this working and to sanity-check the resulting maps by eye before trusting any downstream numbers, since a broken reshape_transform can produce maps that look plausible but are spatially meaningless.

### 4.2 A note on the T2 adaptive attack

torchattacks' built-in FGSM/PGD implementations only accept a single classification objective, so T2 cannot be built by simply calling a library function. Implement a small custom PGD loop whose loss is L = L_attack − λ·CSED(x′), differentiating through both streams and the Grad-CAM extraction. If differentiating through Grad-CAM directly proves awkward, a reasonable first approximation is to instead penalize the L2 distance between intermediate feature activations of the two streams as a differentiable proxy for CSED during the attack, while still measuring true Grad-CAM-based CSED for evaluation afterward. Note this as a known simplification if used.

# 5. Dataset for the Pilot

Phase 0 does not need a large or generically representative dataset — it needs a small, clean, matched real-vs-AI set that lets you compute CSED reliably. Two options, in order of preference:

- Primary: reuse the matched real/AI art set already being built for the artist-classifier project (≈30 AI paintings × 50 artists, matched against real scans with resolution/JPEG/blur equalized per that project's Step 2). This set is art-domain-specific, already being produced, and equalized for the scan-vs-render confound, which removes a known nuisance variable before CSED is even computed. Reusing it also means Phase 0 output plugs directly back into the attribution-based detection project rather than requiring a second dataset-building effort.

- Fallback: a small, fixed slice (roughly 300–500 real and 300–500 AI images) from GenImage or DRCT, used only if the artist-classifier set is not ready in time. This sacrifices the art-domain specificity but keeps the pilot unblocked.

Either way, keep the pilot dataset small on purpose — large-scale coverage is a Phase 1/2 concern, not a Phase 0 one.

# 6. Week-by-Week Execution Plan

## 6.1 Week 1 — Setup, Sanity Checks, and the Observation Question (Q1)

- Set up two separate environments (dependency versions for NPR and UnivFD are likely to conflict) and confirm each detector reproduces its published clean-data accuracy on a small held-out sample before trusting it further.

- Wire up Grad-CAM for NPR (standard) and UnivFD (reshape_transform for ViT); visually inspect a handful of maps for both real and AI images to confirm they look sane before computing anything quantitative.

- Build the CSED computation pipeline: extract E_A(x) and E_B(x) for every clean image, normalize both to a common resolution/scale, and compute cosine distance and JS divergence between them.

- Run the Q1 negative control: split the clean set in half at random, compute CSED-based AUC between the two halves. This should be close to chance — if it isn't, something in the pipeline (likely normalization) is broken, and it needs to be fixed before Week 2 starts.

## 6.2 Week 2 — T1 Attacks and the Hypothesis Question (Q2)

- Generate T1-attacked versions of the clean set using FGSM and PGD (via torchattacks) against each stream independently, at 2–3 perturbation budgets (e.g. ε ∈ {4/255, 8/255, 16/255}) to see how the signal scales with attack strength.

- Compute CSED on the attacked set using the same pipeline from Week 1, with no changes to normalization or metric choice.

- Compare clean-CSED vs. attacked-CSED distributions: run the KS-test, compute AUC of CSED as a clean-vs-attacked classifier, and plot both distributions as histograms.

- Checkpoint: compare the result to the Q2 bar in Section 3. If CSED does not separate clean from T1-attacked images at all, stop here — write up the negative result (Section 10) rather than proceeding to Week 3.

## 6.3 Week 3 — T2 Adaptive Attack and the Gate Decision (Q3) — conditional on Week 2

- Implement the custom adaptive PGD loop described in Section 4.2, using the same perturbation budgets as Week 2 for comparability.

- Generate T2-attacked versions of the clean set and compute CSED exactly as before.

- Compare clean-CSED vs. T2-attacked-CSED: same KS-test and AUC analysis as Week 2.

- Make the gate decision using Section 3's Q3 bar and write the Phase 0 summary (Section 10), regardless of which way the decision goes.

# 7. Deliverables and Artifacts

- Two histograms per comparison (clean vs. T1, clean vs. T2), overlaid, with the AUC and KS-test p-value reported on the plot itself.

- A small gallery of side-by-side Grad-CAM visualizations (Paradigm 1 vs. Paradigm 2, clean vs. attacked) for 6–10 representative images — this is the figure that will anchor any future write-up.

- A short (1–2 page) internal summary stating the Q1/Q2/Q3 results against the pre-registered bars from Section 3, and the resulting go/no-go recommendation.

- The pipeline code itself (data loading, CSED computation, T1/T2 attack generation), kept in a state that Phase 1 can extend directly rather than rewrite.

# 8. Known Risks and Mitigations

- Grad-CAM on a frozen CLIP ViT is easy to get subtly wrong (plausible-looking but spatially meaningless maps). Mitigation: the explicit visual sanity check in Week 1, Day 2, before any quantitative work depends on it.

- Small dataset size (≈1,500 images if using the artist-classifier set) means AUC estimates will have real variance. Mitigation: report confidence intervals (e.g., via bootstrap) alongside point estimates rather than a single AUC number, and treat borderline results (close to the Section 3 bars) as inconclusive rather than as a clean pass or fail.

- Differentiating through Grad-CAM for the T2 attack loop can be technically awkward. Mitigation: the feature-distance proxy noted in Section 4.2, used transparently and flagged as an approximation.

- Dependency conflicts between the NPR and UnivFD repos (different PyTorch/CUDA expectations). Mitigation: separate virtual environments per Section 6.1, Day 1; do not try to force both into one environment.

# 9. Compute and Hardware Estimate

Both detectors are small relative to modern training workloads — NPR is a lightweight CNN and UnivFD only fine-tunes a linear head on frozen CLIP features, so inference and Grad-CAM extraction on ≈2,000–3,000 images (clean + T1 + T2 variants) should comfortably fit on a single consumer or cloud GPU (e.g., an RTX 3090/4090 or a T4/A10 instance) within the 2–3 week window. The dominant cost is PGD/adaptive-PGD generation (10–20 gradient steps per image per budget), not the detectors themselves — budget accordingly if using a shared or rented GPU.

# 10. Decision Tree at the End of Phase 0

- Q1 fails (clean split-half AUC far from 0.5): the pipeline has a bug, most likely in normalization. Fix and re-run Week 1 before drawing any conclusion about the phenomenon itself.

- Q1 passes, Q2 fails (no separation under T1): report a clean negative result. This is useful — it means paradigm-orthogonal explanation divergence does not detect even non-adaptive attacks in this setting, and the full proposal should not be built on it as currently formulated.

- Q1 and Q2 pass, Q3 fails (adaptive attack suppresses the signal): report a partial result. This is the “obfuscated gradients” outcome the earlier reviews warned about — CSED works only against non-adaptive attackers. Worth writing up honestly; do not proceed to the full Phase 1 build-out on the assumption of adaptive robustness.

- Q1, Q2, and Q3 all pass: proceed to Phase 1 as scoped in the main proposal (Section 8.2) — build the calibration model, the learned inference-time classifier, and the full T1/T2/T3 evaluation suite.

# 11. Definition of Done Checklist

- [ ] NPR and UnivFD both reproduce published clean-data accuracy on the pilot sample.

- [ ] Grad-CAM maps visually verified sane for both streams, including the ViT reshape_transform.

- [ ] Q1 negative control run and passed before any attack generation.

- [ ] T1 (FGSM, PGD) attacked set generated at ≥ 2 perturbation budgets.

- [ ] Q2 statistical comparison (KS-test, AUC, bootstrap CI) completed and checked against the pre-registered bar.

- [ ] T2 adaptive attack loop implemented and run, conditional on Q2 passing.

- [ ] Q3 statistical comparison completed and checked against the pre-registered bar.

- [ ] Deliverables from Section 7 produced, including the 1–2 page go/no-go summary.